## PRO-Projects_Modifications
Checklist for handover of Business Critical Documents from Projects/Modifications to Operations D2 - Project Close Out (excl. LCI & Gov Docs)
Projects | [9 empty] | Handover to Operations | [6 empty] | Operations - PRO Modifications |  |  | Operations - PRO Projects
Grouping of Business Critical Documents in project phase | [9 empty] | When |  |  |  |  | How | Who
Document | Description | Comments | Document kind | Discipline (metadata) | Document criticality | Security Class | PRO Modification System | PRO Projects System | Domain | DG 0 | DG 1 | DG 2 | DG 3 | Close-Out | Transfer type | Role/Person | System | Asset level L2 | Asset level L3 | System | Asset level L2 | Asset level L3 | Asset level L4
Self-verification against project deliverable requirements list | The self assessment report shall document how the requirements of the customized check list are met, and contain a conclusion and recommendations for the decision to be made. | Will be LCI on future projects | List | Project Management | Business Critical | AkerBP Internal | Sharepoint | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Documented project organization, including roles and responsibilities description | A project organization sufficient for execution of the project shall be established. Roles, responsibilities and decision rights shall be clearly defined and understood by project team members. Respective BUs shall establish organisations to cover the scope as per mandate. |  | Presentation | Project Management | Non-Busines Crit | AkerBP Internal | Sharepoint | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Authority application plan | Any authority applications and authority communication therein for the project shall be included in the authority application plan. The plan shall also include a register of all regulatory submittals/ approvals worked into the overall project plan. The register shall be updated for each phase. |  | Plan | Project Management | Business Critical | AkerBP Internal | Other | Other | Mods Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Design basis | A Design Basis shall be established and frozen at end of Select stage. The Design Basis shall be subject to "no change" during FEED and Execution. The Design Basis shall as a minimum include: • Reservoir pressure and temperature, fluid composition and chemistry, production profiles • Environmental and geotechnical conditions • Facilities capacities and regularity requirements • Product (oil, gas, condensate etc.) specification | Will be LCI on future projects | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Functional requirements | A Functional Requirements Specification shall be established and frozen at end of Select stage. The Functional Requirements shall be subject to "no change" during FEED and Execution. Functional Requirements shall be developed for relevant installations/systems to be used as a consistent input to the design work. The Functional Requirements shall as a minimum include: • Applicable regulations, codes and standards • Requirements to each system • Operational and maintenance requirements • Drilling and well design • Intervention technology | Will be LCI on future projects | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project execution plan (pep) | A project Execution Plan (PEP) shall be established in Appraise and be a part of the decision support package. PEP shall reflect the project mission, objective, work processes, governing documents, organization, responsibilities, estimates and commitment plans. The project Execution Plan (PEP) shall be finalized/updated before entering the coming gate and reflect the following phase. |  | Plan | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Documentation of the concept screening / selection process | A report shall be prepared describing the concept selection process, giving an account for the selected concept and reasoning for excluding other concepts. |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Integrity due diligence | The project shall verify and document how satisfactory ethics and code of conduct is implemented. |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
IM/IT strategy and plan | The strategy shall describe how the project will ensure an optimal flow of information, and transfer of information to Operations, including the use of IT tools. |  | Plan | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project manual (digital collaboration tool) | A Project Manual shall be established as soon as possible after a project is established, and shall be updated throughout the development of the project. The manual shall be a digital collaboration tool, linking all information relevant for the members of the project and relevant stakeholders. |  | Guideline | Project Management | Non-Busines Crit | AkerBP Internal | Sharepoint | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Decision log | A Decision Log shall be established at project start-up and kept updated until the Change Management process is implemented. |  | Log | Project Management | Business Critical | AkerBP Internal | Sharepoint | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Establish commercial strategy | The strategy shall describe on a high level the commercial alternatives for development of the discovery. The strategy shall be updated at DG2 if relevant. |  | Strategy | Commercial and Finance | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Request for capacity overview | Submitted and reply received in advance of DG1 if alternative is basis for DG1. May be deferred to after DG1 if DG1 is based on a stand-alone alternative |  | List | Commercial and Finance | Non-Busines Crit | AkerBP Internal | Sharepoint | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Establish negotiation team and mandate | The Project Integration Manager request the Asset Development Manager to nominate a negotiation team, and to define its mandate. The mandate shall be approved by the Project Integration Manager |  | Report | Commercial and Finance | Business Critical | AkerBP Internal | Pims DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Request for use | The request is submitted after reply to request for capacity is received. Plan for commercial negotiations is established. |  | Plan | Commercial and Finance | Non-Busines Crit | AkerBP Internal | Other | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Heads of terms for tie-in solutions/transportation | Main terms for tie-in solutions and transportation forming basis for DG2 decisions. |  | Decision memo | Commercial and Finance | Business Critical | AkerBP Internal | Sharepoint | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Fully termed agreements | Agreements consisting of tie-in solution, capacity, transportation of oil/gas, etc. shall be established before sanctioning of a project. |  | Contract - Agreement | Commercial and Finance | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Unitization agreement | Must be established prior to DG3 for fields that requires unitisation. |  | Contract - Agreement | Commercial and Finance | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
“Operational type” appendices | The appendices shall be established and submitted 6 months before First Oil, and shall contain allocation, distribution of value, etc. |  |  | Commercial and Finance | Business Critical | AkerBP Internal | Other | Other | [5 empty] | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Economic analysis | Technical and economical analysis shall be established as requested by the Project Integration Manager, and finally approved by the Project Integration Manager. Value chain Assessment shall be performed in Select. The assessment shall consist of a stochastic analysis of the project economy for the best concepts as basis for final concept selection. The analysis provides risked cash flow. If relevant for submittal of the PDO the analysis should be updated based on request from the Project Integration Manager. |  | Analysis | Commercial and Finance | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Risk management plan | A risk management plan shall be established and updated, consisting of the following elements: - Risk Register - Feasibility Risk Assessment - Concept screening risk assessment - Operational risk reviews (QRA, HAZOP, HAZID, Procedure HAZOP) - Emergency response analyses/ Emergency Preparedness Activities - Environmental Risk Analyses using tools such as ERA acute/MIRA - Map external environmental aspects and risks. - Security analysis of facilities, personnel and information The plan shall be updated for each new phase. |  | Plan | HSSE | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Environmental impact assessment (eia) program | If the project is of such as nature that a PDO submission is required, the KU process shall be initiated; a) Impact screening workshop; b) initiate the KU program process; Impact assessment programme shall be sent on a three month public hearing, 6-9 months before the submittal of the PDO. |  | Plan - Program | HSSE | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Environmental baseline survey | Ahead of the first drilling campaign a baseline study shall be carried out. The survey will be the basis for the future regional 3 yearly environmental surveys |  | Report | HSSE | Business Critical | AkerBP Internal | PIMS DMS | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Environmental risk analyses using tools such as era acute/mira; evaluate the need to update the oil spill contingency plan | To be carried out well in advance of the drilling campaign and before starting up the facility to quantify the consequences well releases. Further, the oil spill response plan shall be evaluated for update |  | Report | HSSE | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
BAT evaluations | Give input to the overall best available technology assessments from an environmental perspective |  | Report | HSSE | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
HSSE strategy and plan | Establish the HSSE management strategy and plan for the project, which will apply to the whole project - including HSSE assurance plan. To be established early, and to be updated when required; as a minimum before each decision. |  | Plan | HSSE | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Establish or update emergency preparedness analyses and plans | The project impact on existing emergency preparedness shall be reviewed and updated as required. Conduct emergency response analyses and develop/update response plans accordingly |  | Plan | HSSE | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Security analysis of facilities, personnel and information | When relevant, projects shall assess security threats and vulnerability for facilities, personnel and information, and prepare security measures as needed. |  | Analysis | HSSE | Business Critical | AkerBP Internal | Other | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Regulatory submittals register | Ensure all regulatory submittals/ approvals are identified early and that this is accounted for in the Project assurance plan/ Project verification plan |  | List | HSSE | Business Critical | AkerBP Internal | Other | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Quality plan | The Quality plan shall describe how the project will perform quality planning, quality control with reference to the company's quality processes and principles, specifying procedures, methods, roles and responsibilities. For smaller projects the Quality Plan may be included in PEP, with a project specific section and reference to a standardized portfolio document. |  | Plan | Quality | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + project name | D2 | Field Development Deliverables | Project Name | Delivery Line
Audit & Verification programme | The Audit & Verification Programme shall have a risk based approach to audits, verifications, self-verifications and over-sight. Internal and contractor/supplier follow-up as deemed necessary by the project to ensure compliance with requirements. For smaller projects the Audit & Verification Programme may be included in PEP, with a project specific section and reference to a standardized portfolio document. |  | Plan - Program | Quality | Business Critical | AkerBP Internal | SPS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Study and engineering reports as per cost estimate class requirements. | The report shall describe the project with its different concept development alternatives considered, reflecting the technical requirements. The report shall describe for each concept the facility functions, production capacities, required uptime and expected lifetime. Further, the report must describe how the intended facilities are operated, developed and maintained in the expected lifetime of the facilities. |  | Report | Facilities Engineering | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Technology assessment / technology qualification program (tqp) | A technology assessment shall be carried out prior to proceeding with the decision to evaluate concepts. If prototypes, new modes of operation, or new technology must be developed, a Technology Qualification Program shall be established and updated as required by 53-000512 AkerBP requirement for Technology Qualification. |  | Plan | Facilities Engineering | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Weight estimate | This document must be developed early and shall be updated continuously as the project moves through the different phases. The document is normally updated on a monthly basis during Execution. | Weight Estimate not created - only weight report | Estimate | Facilities Engineering | Business Critical | AkerBP Internal | Time | Time | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Weight control requirements | This document shall describe how the weight estimate is be built up in the different disciplines, systems, and modules. The document must also describe contingency, following requirements for risk uncertainty (maturity) from DG1 to DG4. The document shall also define the weight expressions, as well as what is included in the different weights e.g. “Gross Weight” “Net weight” “Lifting weight” “Hook Weight” “Dry weight” etc. It is also important that the weight estimate request CoG (Center of Gravity) information on skids, packages and modules, in essence all object to be lifted by cranes, heavy lift vessels etc. |  | Estimate | Facilities Engineering | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Turnaround (TAR) scope | Turnaround/shut down scope shall be established and integrated in the Operations TAR/shut down plan. |  | Plan | Facilities Engineering | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Surveys | Site surveys and seabed surveys shall be arranged to review as-built conditions, identify facilities interfaces, identify any high risk activities such as critical lifts, and identify major tie-ins and shutdown requirements, production impacts and any other constraints, all to inform selection of a concept that can be readily implemented in the existing Brownfield facilities condition. |  | Report | Facilities Engineering | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP | x |  |  |  |  | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
LCI strategy | An LCI strategy shall be established for the project. |  | Strategy | Facilities Engineering | Business Critical | AkerBP Internal | Time | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Document handling strategy | The strategy shall describe how the project will ensure that the level of documentation is reduced to what is absolutely required, as well as minimizing documentation logistics. When an alliance is established, the alliance shall document how it will ensure "good enough" document handling in a procedure. |  | Strategy | Facilities Engineering | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Working environment in design | Develop the Working Environment programme in early Select and update for each decision gate. The programme shall address all relevant issues including chemical risk, mechanical handling, noise exposure, lightning, human/machine interface. WEAC's shall be established/updated. |  | Plan | Facilities Engineering | Business Critical | AkerBP Internal | PIMS DMS | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Constructability review | Construction shall ensure required site surveys are performed, and that brownfield constructability input are supplied prior to DG2 gate. A robust constructability plan should be established, starting prior to DG2, and updated to each gate review. Constructability review shall be conducted to confirm as part of the evaluation of the concept. |  | Plan | Facilities Completion | Business Critical | AkerBP Internal | Other | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Construction Philosophy/ strategy | This document shall describe how the planned completed facility is split into smaller facility components or modules in order to obtain optimum onshore construction and commissioning as well as transport, heavy lift and offshore hook-up and commissioning of each component and the preferred sequence. The strategy must be in accordance with the contract component split and strategy. |  | Strategy | Facilities Completion | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Facilities completion philosophy/ strategy | This document shall describe how the project intends to complete the facility, both onshore and offshore, including a description of acceptance criteria and systems used in the handover process from construction to commissioning, and then on to the final handover to Operations. The document shall also describe in which sequence, when and where the commissioning team expect handover of sub-systems and complete systems from the construction team or contractor(s). The required resources, temporary and/or rental equipment, dependencies of others, as well as a coarse schedule for the scope shall be included. The philosophy/strategy shall reflect that as much of the completion work as possible shall be done onshore due to cost, safety and schedule. |  | Strategy | Facilities Completion | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project specific completion manual | This document shall describe in detail how a specific project shall be completed, with reference to the requirement guidelines in Facility completion philosophy. “Completion” in this case is understood as “ Construction and Commissioning” onshore or offshore including handover to facility owner. To be established in the Select Stage, and finalised in the Improve Stage. |  | Guideline --> User guide | Facilities Completion | Business Critical | AkerBP Internal | PIMS CMS/SPS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Working environment in execution | Working environment and health factors shall be appropriately addressed in offshore execution including construction/hook-up and commissioning |  | procedure | Facilities Completion | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project operational philosophy | The document shall describe how the asset shall be operated. At DG2 the document shall conclude on all key parameters required to ensure no change during Execution. At DG3 the document shall also include specific philosophy for Integrated Operations, maintenance and logistics. If required, the document is updated before start of operations. The philosophy must take into account key operation lessons from other projects. |  | Procedure | Operations | Business Critical | AkerBP Internal | PIMS DMS | Other | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Onshore/offshore organization | The onshore and offshore organization (no. of heads) shall be defined when selecting the concept in order to calculate OPEX. The organization shall be re-evaluated and updated as required for later decision gates. |  | Presentation | Operations | Business Critical | AkerBP Internal | Sharepoint | Other | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Manning studies and recruitment plan for operations | A high level study shall be executed at end of FEED, full recruitment shall be completed before start of operations. |  | Report | Operations | Business Critical | AkerBP Internal | PIMS DMS | Other | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Training program for operation and maintenance personnel | The training program shall be completed and implemented before start of operations. |  | Plan - Program | Operations | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Competence assurance and training for operational personnel | Sufficient levels of competence shall be verified and documented, and the gaps shall be closed before start of operations. |  | Report | Operations | Business Critical | AkerBP Internal | PIMS DMS | Other | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Operating and emergency procedures | Covers all procedures and other operational documentation required to support Operations | Will be LCI on future projects | Procedure | Operations | Business Critical | AkerBP Internal | PIMS DMS | Time | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Maintenance engineering analysis, plans, programs, systems spare parts and procedures | Part of the Project Operational Philosophy until the project is sanctioned. Detailed in a separate document before start of operations. | Will be LCI on future projects | Analysis, Plan, program, SPIR and Procedure | Operations | Business Critical | AkerBP Internal | PIMS DMS | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Logistics strategy (base, helicopter, supply) | Part of the Project Operational Philosophy until the project is sanctioned. Detailed in a separate document before start of operations. |  | Strategy | Operations | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Start-up execution manual | The start-up execution manual shall be established and implemented. | Will be LCI on future projects | Guideline | Operations | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Operations readiness plan | The Operations Readiness Plan shall be completed prior to DG4. |  | Plan | Operations | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Benchmarking against comparable projects / facilities | Prior to DG3, the requirement to use a 3rd party for the benchmark shall be considered. |  | NA | Project Services | Business Critical | AkerBP Internal | Other | Other | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project assurance plan | The Project Assurance Plan shall include all activities, reviews, audits necessary to ensure project compliance at all stages. |  | Plan | Project Services | Business Critical | AkerBP Internal | SPS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Decision support form/package/memorandum |  |  | Dossier - Decision support pachage | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Technical note |  |  | Dossier - Decision support pachage | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Evaluations | notes/reports |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Clarifications | notes/reports |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Analysis | (Ship collision, technical gap) |  | Analysis | Facilities Engineering | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Safeop |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Test results | reports, notes, pictures etc |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Presentations |  |  | Presenatation | Project Management | Non-Busines Critical | AkerBP Internal | Sharepoint | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Visualisation files |  |  |  | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
RACI matrixes |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Safety milestone overview |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
HAZID and emergency preparedness |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Health compliance check list |  |  | List | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Administration procedure |  |  | Procedure | Facilities Engineering | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Compliance integrity strategy |  |  | Plan | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Marine procedures |  |  | Procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Main drilling and wells programme |  |  | Plan - Program | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Shallow gas pilot hole drilling program |  |  | Plan - Program | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Well specific drilling & completion program |  |  | Plan - Program | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Well specific decision paper |  |  | Decision | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Drilling & Wells approval for concent |  |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Drilling & Wells approval for discharge |  |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Final well report drilling |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Intervention position paper |  |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Well life predictions/assumptions |  |  | Prediction/Assumption | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Testprosedyre for brønnbarrierer |  |  | Procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Statement of requirements (sor) |  |  | Procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Company provided items (cpi) documentation |  | Can also be stored in other systems | NA | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Overall procurement strategy (ops) |  |  | Plan | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Drilling and wells mandate |  |  | Mandate | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Drilling & Wells approval for expenditure |  |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Drilling & Wells hand-over document (asset to d&w operations) |  |  | Report | Facilities Engineering | Business Critical | AkerBP Internal | Sharepoint | Sharepoint | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Subsurface evaluation |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | AKBP |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Early engineering document & drawings |  |  | NA | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Transport & installations document & drawings |  |  | NA | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Minutes of meetings |  |  | Minutes of Meeting | Project Management | Business Critical | AkerBP Internal | Pims Meetings | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Integrated offshore huc plan |  |  | Plan | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Onshore support strategy |  |  | Plan | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Design review report |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Pims Lessons Learned | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project review report |  |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | Pims Meetings | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Study reports (unpriced) |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Study reports (priced) |  |  | Report | Project Management | Business Critical | Confidential | Sharepoint | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Scope of work | All scope of work generated in projects |  | Terms of References - Scope of work | Facilities Engineering | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Progress status reports |  |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Correspondence |  |  | Correspondence | Project Management | Business Critical | AkerBP Internal | Pims DMS Correspondence Register | Pims DMS Correspondence Register | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Mobilization plan |  |  | Plan | Project Management | Business Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project roadmap |  |  | Report | Project Management | Business Critical | AkerBP Internal | Sharepoint | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project initiation request (pir) |  |  | Proposal | Project Management | Non-Busines Critical | AkerBP Internal | Sharepoint | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Commissioing plan |  |  | Plan | Facilities Completion | Business Critical | AkerBP Internal | Sharepoint | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Construction plan |  |  | Plan | Facilities Engineering | Business Critical | AkerBP Internal | Sharepoint | Pims DMS Correspondence Register | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Flow assurance reports |  |  | Report | Facilities Engineering | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Bridging documents |  |  | Procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Barrier managment documnets |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | Sharepoint | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
DG0 presentation |  |  | Presentation | Project Management | Non-Busines Critical | AkerBP Internal | PIMS DMS | Sharepoint | Mods Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
DG3 presentation |  |  | Presentation | Project Management | Non-Busines Critical | AkerBP Internal | PIMS DMS | Sharepoint | Mods Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Project execution proposal | Created by Modifications Alliance on Cat 4 projects |  | Proposal | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Mods Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Close out report |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Codes & standard |  |  | procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Weight report |  |  | Report | Facilities Engineering | Business Critical | AkerBP Internal | Time | Other | Mods Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
PEER review report |  |  | Report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | All |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Alliance administration | Alliance level |  | Procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Alliance execution manual | Alliance level |  | Procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Alliance templates, edting and revision control | Alliance level |  | procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Contract administration procedure | Alliance level |  | procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Cost procedure | Alliance level |  | Procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Diving experience report | Alliance level |  | report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Pipe stress report | Alliance level |  | report | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
LCI execution plan | Alliance level |  | Plan | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
MLC/estimating procedure | Alliance level |  | Procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Planning procedure | Alliance level |  | procedure | Project Management | Business Critical | AkerBP Internal | PIMS DMS | PIMS DMS | Subsea Alliance |  |  |  |  | x | Manual transfer | Information Steward | D2 | Modification Project | AFA/ SAP ID + Project Name | D2 | Field Development Deliverables | Project Name | Delivery Line
Note on X4: Tor Solberg: Delivery lines: Facilities Wellhead Platform Alliance Subsea Alliance T&I Modification Alliance

## Drop down lists (hidden)
Security Class | Document | Document Group | Domain | System
Secret | Business Critical | Project Management | AKBP | Pims DMS
Confidential | Non-Busines Critical | Commercial and Finance | AKSO | Pims TQ
AkerBP Internal | LCI | HSSE | Mods Alliance | Pims Completion (CMS)
Public | Gov Doc | Quality | All | Pims Non-Conformacy/ Deviation
|  | Facilities Engineering | Subsea Alliance | Project and supplier
|  | Facilities Completion |  | Pims DMS Correspondence Register
|  | Operations |  | Pims Risk
|  | Project Services |  | Pims MoC
|  | Project Assurance |  | Pims VO/VOR
Pims QA
Pims Interface
Pims Lessons Learned
Pims HAZOP
Pims Meetings
Sharepoint
Time
Other
Pims Actions